Joint Action: Improving Quality in HIV Prevention

Work Package (WP) Plan

| Work Package | WP7 Quality Principles and Criteria |
| --- | --- |
| Last Updated | 11.10.2013 |
| Work Package Leader | Federal Centre for Health Education (BZgA), Germany |
| Work Package Partners | Associated partners: Aids Help Vienna (AHW), National Institute for Health Development Estonia (NIHD), SKUC, Hellenic Centre for Disease Control and Prevention (KEELPNO), Slovak Medical University (SMU), Health Service Executive Ireland (HSE), Sexual Health Centre (SHC) Collaborating partner: University of Applied Sciences Northwestern Switzerland (FHNW) |

Working days of WP partners

| BZgA | 234 days (Coordination) 80 days (Project assistant) |
| --- | --- |
| SMU | 140 days |
| AHW | 106 days |
| KEELPNO | 99 days |
| HSE | 80 days (no participation anymore in WP7) |
| NIHD | 70 days |
| SKUC | 60 days |
| SHC | 10 days |
| Total staff working days | 879 |

Further budget allocated to WP7

- Each partner: travel costs and subsistence allowances allocated to their budget to participate in three WP7 meetings

- BZgA: 3.000 Euros for participation of collaborating partners/ Advisory Group members/ members of the Scientific Reference Panel in meetings

- BZgA: subcontract: tbd

- AHW: subcontract: 5.000 Euros for expert (including travel costs)

- BZgA: 2.000 Euros for layout and printing of the Charter

- BZgA: 500 Euro for fees to participate at an external conference

Short WP Description

WP7 collects and analyses QA/QI experiences and results of participating HIV prevention programs and projects and develops an agreed Charter for Quality in HIV Prevention including quality principles and criteria for HIV prevention in general and, where appropriate, for specific priority populations.

WP Objective(s)

By the end of the Joint Action, develop, adopt and disseminate a ‘Charter for Quality in HIV Prevention’ with agreed quality principles and criteria for use in assessing and improving the quality of HIV prevention programs and projects.

Detailed WP Description

WP7 develops general quality principles and criteria from the application of QA/QI tools, refines them in light of relevant literature and consults with partners to produce an agreed ‘Charter for Quality in HIV Prevention’, to be submitted to and adopted by MS and civil society through the HIV Think Tank and Civil Society Forum.

WP7 will collect data using desk review, survey instruments developed in consultation with WP6 participants and through focus groups conducted in combination with the four regional WP5 follow-up training workshops. WP7 will also liaise with WP6 to include their findings on political, structural, financial and social enablers and barriers to quality prevention. This work and other significant results will also form the basis for scientific publications led by this WP. The WP will make relevant scientific evidence and information available to partners through regular research updates at meetings and through networking communications.

It will develop and maintain links to and exchange with relevant European initiatives (e.g. research initiatives such as ECDC’s behavioural and second generation surveillance toolkit, EMCDDA QA/QI activities, EMIS and intervention projects such as COBATEST, SIALON, Everywhere, H-Cube, Sunflower, IMPACT) and will pursue emerging synergies. The WP will convene a Scientific Reference Panel (SRP) that reviews current research on and the practice of HIV prevention in relation to the Joint Action’s focus on quality.

KEY ACTIVITIES: 1) Design data collection instruments and liaise with WP6 to collect data; 2) analyse the results of practical application for emerging themes; 3) identify and document quality principles and criteria for HIV prevention; 4) draft, consult on and finalise the Charter for Quality in HIV Prevention; 5) convene the SRP; 6) provide scientific advice to the project; 7) liaise with research and review projects; 8) identify and present regular updates from scientific and grey literature; and 9) lead the writing and publication of scientific articles on project results.

WP Milestones and Deliverables

| Deliverables | Milestones | Due Date |
| --- | --- | --- |
| QA/QI in HIV Prevention: Charter for Quality in HIV Prevention |  | Month 33, November 2015 |
| QA/QI in HIV Prevention: Technical and Financial Reports including final version of Charter |  | M36, February 2016 |
|  | Terms of Reference, membership list for Scientific Reference Panel (SRP) | Month 4, June 2013 |
|  | Draft data collection, analysis and consultation plan | Month 8, October 2013 |
|  | Final data collection, analysis and consultation plan | Month 10, December 2013 |
|  | Data collection completed | Month 26, April 2015 |
|  | Scientific article(s) submitted for publication | Month 33, November 2015 |

WP Overview and general comments

Important collaborations:

WP2: Corporate design and dissemination of Charter

WP3: To plan the WP7 specific data collection (which data we need for formulating quality principles and criteria as the result of the practical application) and include it in the WP3 assessment plan as basis for Charter,

WP5: To conduct focus groups in combination with the four regional WP5 follow-up training workshops

WP6: To develop survey instruments in consultation with WP3 and apply them to WP6 participants. Liaise with WP6 to include their findings on political, structural, financial and social enablers and barriers to quality prevention. This work and other significant results will also form the basis for scientific publications led by this WP.

WP8: The Charter will be the technical basis for the policy kit. Results of the practical application will be one root for the Charter and the Charter will be one root for the policy kit. WP7 and WP8 constantly inform each other about the state of the art and share draft versions of both deliverables.

WP7 is highly dependent on a meaningful data collection with the participants of WP6 conducted by WP3.

The inclusion of the results in the knowledge base collected by literature reviews, focus groups etc. will be challenging.

The phrasing of the principles and criteria needs to be not too generic and not to specific

Detailed Annual Work Plans

Work Plan Year 1 (March 2013 - February 2014)

| Month | Activity | Tasks | Responsible |
| --- | --- | --- | --- |
| June 2013 | Scientific Reference Panel | Develop Terms of Reference | WP7 lead |
| August 2013 | Scientific Reference Panel | Convene SRP SRP adopts Terms of Reference | WP7 lead |
| 7-8 October 2013 | First WP Meeting in Vienna | Organisation of first WP7 meeting Agreement about draft data collection, analysis and consultation plan Agreement about literature review Agreement of draft approach for Charter First discussion about focus groups | WP7 lead/ AHW and all WP7 partners |
| 16-17 October 2013 | Draft data collection, analysis and consultation plan | Discussion with WP6, WP3 and the SG about the draft data collection, analysis and consultation plan during the second SG meeting | WP7 lead, WP6 lead,WP3 lead and SG) |
| November 2013 | Draft data collection, analysis and consultation plan | Development of indicators by WP3 | WP3 |
| November 2013 | Offer for literature review | Send the offer for the literature review (provided by subcontractor Frank Amort) to WP7 partners and SRP members for comment | WP7 lead, all WP7 partners, SRP |
| December 2013 | Start of literature review | Subcontractor Frank Amort starts literature review according to guidelines of WP7 | Subcontractor Frank Amort |
| February 2014 | Final data collection and consultation plan |  | all WP7 partners |

Notes:

(space for describing important things that the table does not show, e.g. prerequisites for tasks)

Problems and solutions

(e.g. anticipated delays, expected difficulties and how you will deal with them)

| Barrier | Responses | Responsible | Due Date |
| --- | --- | --- | --- |

Work Plan Year 2 (March 2014 - February 2015)

| Month | Activity | Tasks | Responsible |
| --- | --- | --- | --- |
| February/ March 2014 | Second WP7 meeting and first SRP meeting in Cologne (tbd: + WP3 and WP6) | Interim reporting of literature review Discuss evaluation phase (how we plan to derive principles and criteria from literature and data analysis) Discuss on approach and structure of Charter, Discuss WP7 reporting Discuss regional consultation and focus groups | WP7 lead, all WP7 partners, SRP, WP3 lead, WP6 lead |
| May 2014 | Interim literature review | First draft analysis and report from literature review | Frank Amort |
| June 2014 | Final version literature review |  |  |
| From June 2014 on | Further analysis of literature review | Derive principles and criteria and evidence from the literature review | all WP7 partners |
| October 2014 (and January/February 2015) | Regional consultation/ focus groups | Focus groups with trainers at the four follow-up regional training workshops | all WP7 partners, WP5 lead, WP6 lead + tbd |
| December 2014 | Scientific article | Scientific article on literature review | all WP7 partners and Frank Amort |

Notes:

Problems and solutions

(e.g. anticipated delays, expected difficulties and how you will deal with them)

| Barrier | Responses | Responsible | Due Date |
| --- | --- | --- | --- |

Work Plan Year 3 (March 2015 – February 2016)

| Month | Activity | Tasks | Responsible |
| --- | --- | --- | --- |
| January/February 2015 | Regional consultation/ focus groups | Focus groups with trainers at the four follow-up regional training workshops | all WP7 partners, WP5 lead, WP6 lead + tbd |
| April 2015 | Data collection completed | Start data analysis: development of principles and criteria for the data analysis report | all WP7 partners |
| June 2015 | Third WP7 meeting and second SRP meeting | Discuss about: data analysis, development of principles and criteria, scientific articles | all WP7 partners and SRP |
| October/ November 2015 | Charter for Quality in HIV prevention | First final version based on results of data analysis and literature review | all partners of WP7 |
| October/ November 2013 | Presentation of Charter at final conference | Adoption by Quality Action partners and external participants | all WP7 partners/ all Quality Action partners |
| November 2015 | Scientific articles | Scientific article on data collection in WP7 and on Quality Action as a whole | All partners of WP7/ all partners of Quality Action |
| December 2015 | Presentation of Charter to TT and CSF | Adoption of the Charter | WP7 lead |
| December-January 2016 | Charter for Quality in HIV prevention | Translation of Charter | All partners of Quality Action |
| February 2016 | Charter for Quality in HIV prevention | Revised final version including translations |  |

Notes:

Problems and solutions

(e.g. anticipated delays, expected difficulties and how you will deal with them)

| Barrier | Responses | Responsible | Due Date |
| --- | --- | --- | --- |